
United Nations

A/59/619

 [image: image1.wmf]

General Assembly

Distr.: General

17 December 2004

Original: English

[image: image1.wmf]





Fifty-ninth session

Agenda item 137

Financing of the United Nations Mission for the

Referendum in Western Sahara


Performance report on the budget of the United Nations Mission for the Referendum in Western Sahara for the period from 1 July 2003 to 30 June 2004



Report of the Secretary-General

Contents



Paragraphs
Page

I. 
Introduction

1–2
3

II. 
Mandate performance

3–6
3

III. 
Resource performance

7

A. Financial resources

7

B. Other income and adjustments

8

C. Expenditure for contingent-owned equipment: major equipment and self-sustainment

8

D. Value of non-budgeted contributions

8

IV. 
Analysis of variances

7–22
9

V. 
Actions to be taken by the General Assembly

23
11



I.
Introduction

1.
The budget for the maintenance of the United Nations Mission for the Referendum in Western Sahara (MINURSO) for the period from 1 July 2003 to 30 June 2004 was set out in the report of the Secretary-General of 20 December 2002 (A/57/675 and Corr.1) and amounted to $44,239,400 gross ($40,920,800 net), inclusive of budgeted voluntary contributions in kind of $1,776,100. It provided for 203 military observers, 27 military contingents, 26 civilian police, 184 international staff, 113 national staff and 6 observers from the African Union. The Advisory Committee on Administrative and Budgetary Questions, in paragraph 30 of its report dated 3 April 2003 (A/57/772/Add.2), recommended that the General Assembly appropriate $41,529,500 gross for the period from 1 July 2003 to 30 June 2004.

2.
The General Assembly, by its resolution 57/331 of 18 June 2003, appropriated an amount of $41,529,500 gross ($38,488,500 net) for the maintenance of the Mission for the period from 1 July 2003 to 30 June 2004. The total amount has been assessed on Member States.


II.
Mandate performance

3.
The mandate of MINURSO was established by the Security Council in its resolution 690 (1991). The mandate for the performance period was provided by the Council in its resolutions 1485 (2003), 1495 (2003), 1513 (2003), 1523 (2004) and 1541 (2004).

4.
The Mission is mandated to help the Security Council achieve an overall objective, namely, to enable the people of Western Sahara to choose, freely and democratically, between independence and integration with Morocco.

5.
Within this overall objective, the Mission has, during the performance report period, contributed to a number of accomplishments by delivering related key outputs, shown in the frameworks below. These frameworks are grouped by components: substantive civilian, military and support. 

6.
The 2003/04 period is the first period for which the Mission was able to assess its performance against the planned results-based frameworks set out in the 2003/04 budget. The performance report compares the actual indicators of achievement, the extent to which actual progress has been made during the period against the expected accomplishments, with the planned indicators of achievement, and compares the actually completed outputs with the planned outputs.

Component 1: substantive civilian

Expected accomplishment 1.1: Progress towards political settlement on the status of Western Sahara

Planned indicators of achievement
Actual indicators of achievement





Increased dialogue between and among parties to the conflict
No negotiations between parties to the conflict

Planned outputs
Completed
 (number or yes/no)
Remarks





Regular consultations by the Special Representative of the Secretary-General with parties and diplomatic corps in the region
Yes


Facilitated meetings by the Special Representative of the Secretary-General between and among the parties
No
There were no direct negotiations between the parties to the conflict during the reporting period

Reports of the Secretary-General to the Security Council
3


Updated secured list of voters for the referendum in Western Sahara
No
Identification Commission was suspended

Conducted hearings on admissibility and substance for appeals
No
Identification Commission was suspended

Completed Identification Commission manuals on appeals
No
Identification Commission was suspended

Secured registered voter files and other sensitive Identification Commission materials
Yes
All sensitive files have been transferred to the United Nations Office at Geneva

Regular press briefings
No
Only ad hoc press briefings were conducted

Expected accomplishment 1.2: Progress towards resolution of the humanitarian aspects and human rights issues of the conflict

Planned indicators of achievement
Actual indicators of achievement





Increase in donor aid. Family visits and regular exchanges and mail/telephone communications between refugees and their families in the Territory
•
With agreement of the parties, the telephone communication programme restarted in 2 of the 5 refugee camps

•
806 people from both sides participated in the family visit programme

Reduction in the number of prisoners of war and persons unaccounted for
•
Three prisoner releases. Number of prisoners of war held reduced from 900 to 412

Planned outputs
Completed
(number or yes/no)
Remarks





Regular consultations between the Special Representative of the Secretary-General and United Nations agencies to assist in improving adequacy of food delivery and begin implementation of cross-border confidence-building initiatives
Yes


Regular consultations between Special Representative of the Secretary-General and International Committee of the Red Cross (ICRC) to facilitate increase in number of prisoners of war released and decrease in the number of persons unaccounted for
Yes
Consultations with ICRC were held informally via telephone and e-mail


Component 2: military

Expected accomplishment 2.1: Ensured compliance of the parties with the ceasefire agreements

Planned indicators of achievement
Actual indicators of achievement





No violations of ceasefire agreements
2 violations

Unrestricted movement of United Nations military observers
Only minor limitations and restrictions to ground patrols and air reconnaissance

Reduction in landmines and unexploded ordnance
295 unexploded ordnance

Planned outputs
Completed
 (number or yes/no)
Remarks





Regular meetings between mission Force Commander, team site commanders and parties to the conflict
94


470 ground and 35 air patrols conducted per month
489
Ground patrols. Higher number owing to unscheduled patrols for the monitoring of unexploded ordnance destruction


34
Air patrols

Reports on locations for destruction of suspected mines/unexploded ordnance sites
241


Component 3: support

Expected accomplishment 3.1: Increased efficiency and effectiveness in supporting the Mission

Planned indicators of achievement
Actual indicators of achievement

Increased level of satisfaction expressed by 
client offices with support provided
•
Problems identified in the daily managers’ meetings resolved

Planned outputs
Completed 
(number or yes/no)
Remarks

Personnel, goods and equipment transported by road, sea and air
20 090
Passengers

Cargo moved by air
1 743
Tons

Cargo moved by land — 25 000 medium truck km
4 000
Tons

298 United Nations vehicles maintained
Yes


8 km X 300m runways maintained
Yes


Premises and facilities managed, maintained and upgraded
16

29
Facilities in 12 locations

Prefabricated buildings replaced

United Nations-owned generators managed and maintained
53


Supply items distributed
Yes


Medical supplies provided and vehicles maintained
Yes


Maintained medical evacuations capability
Yes


Daily uninterrupted communications and information technology support services provided
Yes
Information technology support provided for 465 users in 12 different locations

Installed additional V-Sat stations

Staff administered, recruited and trained
255

9

225
Total of average numbers of 145 international and 110 national staff

Average number of civilian police

Military personnel


III.
Resource performance


A.
Financial resources

(Thousands of United States dollars. Budget year is from 1 July 2003 to 30 June 2004.)

 

 
Variance


Apportionment
Expenditure
 
Amount
Percentage

Category
(1)
(2)

(3) = (1) - (2)
(4) = (3) ÷ (1)

Military and police personnel






Military observers
5 448.8 
5 454.7 

(5.9)
(0.1)

Military contingents
673.4 
769.8 

(96.4)
(14.3)

Civilian police
595.4 
270.8 

324.6 
54.5 

Formed police units
— 
— 

— 
— 

Subtotal
6 717.6 
6 495.3 

222.3 
3.3 

Civilian personnel






International staff
18 524.0 
15 903.9 

2 620.1 
14.1 

National staff
1 767.8 
1 569.0 

198.8 
11.2 

United Nations Volunteers
— 
— 

— 
— 

Subtotal
20 291.8 
17 472.9 

2 818.9 
13.9 

Operational costs






General temporary assistance
— 
— 

— 
— 

Government-provided personnel
120.0 
40.4 

79.6 
66.3 

Civilian electoral observers
— 
— 

— 
— 

Consultants
10.0 
10.5 

(0.5)
(5.1)

Official travel
347.3 
322.9 

24.4 
7.0 

Facilities and infrastructure
2 297.6 
2 169.2 

128.4 
5.6 

Ground transportation
3 803.8 
3 462.3 

341.5 
9.0 

Air transportation
5 511.8 
6 432.1 

(920.3)
(16.7)

Naval transportation
— 
— 

— 
— 

Communications
676.6 
827.8 

(151.2)
(22.4)

Information technology
778.5 
739.9 

38.6 
5.0 

Medical
88.0 
90.8 

(2.8)
(3.2)

Special equipment
15.0 
10.8 

4.2 
28.2 

Other supplies, services and equipment
871.5 
775.9 

95.6 
11.0 

Quick-impact projects
— 
— 

— 
— 

Subtotal
14 520.1 
14 882.6 

(362.5)
(2.5)

Gross requirements
41 529.5 
38 850.8 

2 678.7 
6.5 

Staff assessment income
3 041.0 
2 442.8 

598.2 
19.7 

Net requirements 
38 488.5 
36 408.0 

2 080.5 
5.4 

Voluntary contributions in kind (budgeted)a
1 776.1 
3 084.0 

(1 307.9)
(73.6)

Total requirements
43 305.6 
41 934.8 

1 370.8 
3.2 


a
Includes $329,697 from the Government of Algeria, $2,554,330 from the Government of Morocco and $200,000 from the Frente POLISARIO.


B.
Other income and adjustments

(Thousands of United States dollars)

Category
Amount




Interest income 
68.0

Other/miscellaneous income
204.0

Prior-period adjustments
3.0

Savings on or cancellation of prior-period obligations
919.0


Total
1 194.0


C.
Expenditure for contingent-owned equipment: major equipment and self-sustainment

(Thousands of United States dollars)

Category
Expenditure




Major equipment



Military contingents




Major equipment
88.0

Self-sustainment
—

Total
88.0

Mission factors
Percentage
Effective 
date
Last review
date

Applicable to Mission area





Extreme environmental condition factor
2
—
—


Intensified operational condition factor
3 
— 
— 


Hostile action/forced abandonment factor
1 
— 
— 


D.
Value of non-budgeted contributions

(Thousands of United States dollars)

Category

Actual value





Status-of-forces agreement

3 184.6

Voluntary contributions in kind (non-budgeted)

— 



Total

3 184.6


IV.
Analysis of variances


Variance

Military observers
($5.9)
(0.1%)

7.
Additional requirements were due to air fare increases resulting in higher cost of travel of military observers.


Variance

Military contingents
($96.4)
(14.3%)

8.
Additional requirements resulted from the obligation of funds for troop cost reimbursement owed for fiscal year 2001/02, since insufficient funds had been obligated for that period.


Variance

Civilian police
$324.6
54.5%

9.
The unutilized balance resulted from the closure of the civilian police component in December 2003. All civilian police were repatriated to their respective countries by 31 December 2003, following the transfer of the Identification Commission files and materials to the United Nations Office at Geneva.


Variance

International staff
$2,620.1
14.1%

10.
The unutilized balance was attributable to the completion of the work of the Identification Commission staff on 31 December 2003. The 25 related posts had been budgeted for 12 months.


Variance

National staff
$198.8
11.2%

11.
The unutilized balance was due mainly to the fact that the salaries were budgeted at G-4/1, whereas the actual staff salaries were close to the G-3/1 scale.


Variance

Government-provided personnel
$79.6
66.3%

12.
The unutilized balance was due mainly to the delay in the replacement of African Union observers.


Variance

Consultants
($0.5)
(5.1%)

13.
Additional requirements were attributable to the hiring of a consultant for the people’s management training course, held in May 2003, funds for which had inadvertently not been obligated in the prior period.


Variance

Official travel
$24.4
7%

14.
The unutilized balance was due mainly to the standstill political situation in the region which resulted in lower than expected official travel by the Special Representative of the Secretary-General.


Variance

Facilities and infrastructure
$128.4
5.6%

15.
The unutilized balance resulted primarily from a newly negotiated systems contract which led to the lower than budgeted cost of prefabricated facilities.


Variance

Ground transportation
$341.5
9.0%

16.
The unutilized balance was attributable mainly to the transfer of vehicles from the United Nations Iraq-Kuwait Observation Mission, resulting in reduced requirements under acquisition of vehicles.


Variance

Air transportation
($920.3)
(16.7%)

17.
The additional requirements were due mainly to the rental cost of three 
MI-8MTV helicopters which replaced three MI-8MT helicopters for operational and safety reasons, as MI-8MTV helicopters are more appropriate for desert conditions.


Variance

Communications
($151.2)
(22.4%)

18.
The additional requirements resulted primarily from the increase in the number of satellite Earth stations from 4 to 11. These seven additional stations, provided mainly from United Nations reserve, led to the extension of full information and communication technology services to remote team sites, resulting in overexpenditure under commercial communications.


Variance

Information technology
$38.6
5.0%

19.
The unutilized balance was due mainly to the completion of the work of the Identification Commission, resulting in reduced costs for information technology services.


Variance

Medical 
($2.8)
(3.2%)

20.
The additional requirements were attributable to the provision of specialized medical consultation services obtained from private providers.


Variance

Special equipment
$4.2
28.2%

21.
The unutilized balance was due to reduced requirements for metal detectors, as they were provided by the United Nations Logistics Base. The Mission had to pay the freight cost only.


Variance

Other supplies, services and equipment
$95.6
11.0%

22.
The unutilized balance was due mainly to the completion of the work of the Identification Commission, which resulted in reduced requirements for rations.


V.
Actions to be taken by the General Assembly

23.
The actions to be taken by the General Assembly in connection with the financing of MINURSO are:


(a)
To decide on the treatment of the unencumbered balance of $2,678,700 with respect to the period from 1 July 2003 to 30 June 2004;


(b)
To decide on the treatment of other income for the period ended 
30 June 2004 amounting to $1,194,000 from interest income ($68,000), other/miscellaneous income ($204,000), prior-period adjustments ($3,000) and savings on or cancellation of prior-period obligations ($919,000).


Summary


	The present report contains the performance report on the budget of the United Nations Mission for the Referendum in Western Sahara (MINURSO) for the period from 1 July 2003 to 30 June 2004.


	The total expenditure for MINURSO for the period from 1 July 2003 to 30 June 2004 has been linked to the Mission’s objective through a number of results-based frameworks, grouped by components, namely, substantive civilian, military and support.





Performance of financial resources


(Thousands of United States dollars. Budget year is from 1 July 2003 to 30 June 2004.)








�
�
�
Variance�
�
Category�
Apportionment�
Expenditure�
�
Amount�
Percentage�
�
Military and police personnel �
6 717.6 �
6 495.3 �
�
222.3 �
3.3 �
�
Civilian personnel�
20 291.8 �
17 472.9 �
�
2 818.9 �
13.9 �
�
Operational requirements�
14 520.1 �
14 882.6 �
�
(362.5)�
(2.5)�
�
	Gross requirements�
41 529.5 �
38 850.8 �
�
2 678.7 �
6.5 �
�
Staff assessment income�
3 041.0 �
2 442.8 �
�
598.2 �
19.7 �
�
	Net requirements�
38 488.5 �
36 408.0 �
�
2 080.5 �
5.4 �
�
Voluntary contributions in kind (budgeted)�
1 776.1 �
3 084.0 �
�
(1 307.9)�
(73.6)�
�
	Total requirements�
43 305.6 �
41 934.8 �
�
1 370.8 �
3.2 �
�






Human resources incumbency performance








Category�
�Approved a�
Planned�(average)�
Actual�(average)�
Vacancy rate�(percentage)b�
�
Military observers�
203�
203 �
198 �
2.3 �
�
Military contingents�
27�
27�
27�
0.3�
�
Civilian policec�
81�
26 �
9 �
64.1 �
�
International staffc�
300�
184�
145�
21.0�
�
National staff�
113�
113 �
110 �
2.9 �
�
Government-provided personnel�
10�
6 �
4 �
33.3 �
�



	a Represents the highest level of authorized strength.


	b Based on monthly incumbency and planned strength. 


c As a result of the suspension of the activities of the Identification Commission, budgetary provision was made for only 26 civilian police and 184 international staff posts. However, following the transfer of the Identification Commission files and materials to the United Nations Office at Geneva, all personnel of the Identification Commission and the civilian police component responsible for the protection of the files and materials were repatriated and their work was suspended on 31 December 2003.





	The actions to be taken by the General Assembly are set out in section V of the present report.








	�	Resource variance amounts are expressed in thousands of United States dollars.





�PAGE \# "'Page: '#'�'"  ��<<ODS JOB NO>>N0465553E<<ODS JOB NO>>


<<ODS DOC SYMBOL1>>A/59/619<<ODS DOC SYMBOL1>>


<<ODS DOC SYMBOL2>><<ODS DOC SYMBOL2>>





04-65553 (E)    070205

*0465553*

10



11


